## Go live check list
Timeline | Task | Task priority | Task Status | Comments
Mid October | Receive reports to check approvers on eExpenses Following the delay to the launch of eExpenses, we recognise that some information on delegated approvers may need updating. The Finance division will issue reports for review to the User Access Dashboard folders (with notification and instructions). Arrange to review and update in time for go-live in consultation with project team | Essential
| Receive comms pack The eExpenses Comms Pack contains resources to support you and your team in communicating and launching eExpenses in your department. Updated documents will be issued. | Essential
Four weeks before go live | Prepare admin team for launch It is recommended that those involved in the process review the approver training available at: https://finance.admin.ox.ac.uk/eexpenses-training-and-support | Recommended
| Prepare admin team for launch Supplementary material is available if required including: Introductory video: https://www.youtube.com/watch?v=bjUcl-KwF1E Quick reference guides: How to videos: https://finance.admin.ox.ac.uk/how-to-videos-2 HAF webinar (2020): https://web.microsoftstream.com/video/a47d44b2-daab-4cc2-b332-b4a47d3c04df?referrer=https:%2F%2Fofficewebapps.nexus.ox.ac.uk%2F PA webinar (2020): https://web.microsoftstream.com/video/ebf64299-5903-45d2-a9b5-ec224e392266 Demo: https://web.microsoftstream.com/video/ebf64299-5903-45d2-a9b5-ec224e392266 | Optional
| Raise awareness of launch in the department Amend and use the template posters (either physically or share electronically) (supplied separately) | Recommended
| Raise awareness of launch in department | Recommended
| Raise awareness of launch in the department Use template for departmental presentations (supplied separately) | Optional
| Consider if any cost centres or project tasks are ineligible for expenses In April 2020, an exercise was undertaken in which departments could specify cost centres and project tasks which should not have expenses charged to them. These are flagged in Oracle and not present in eExpenses. If you wish to make any changes to which cost centres/project tasks are eligible or ineligible to have expenses charged, please complete the appropriate form with details: https://finance.admin.ox.ac.uk/maintaining-roles-and-data-in-eexpenses#collapse2741466 | Recommended
2 weeks before go live | Notification to claimants | Essential
| Claimant Sessions Forward claimants session invites on to claimants | Recommended
| Consider briefing claimants on coding When completing a claim in eExpenses, claimants will be asked to specify to which code items should be charged. They can search by code or first word of cost centre name/project short name, and frequently used items will appear in their favourites in due course. If claimants are not familiar with their codes, you may wish to brief them. | Optional
| Notification to approvers | Essential
Go live day | Confirm to claimants that the system is live | Essential
Send out go live email using template text which includes the link to the live system
Send out countdown email
Send the appropriate template email to approvers based on the approvers reports that you have updated and submitted to the project team
From 4 weeks before go live, amend and use template text in departmental comms e.g. newsletters, bulletins as required
Amend and use template text to send 4 week countdown email
This text can be amended and used more than once during the run up to go live
PowerPoint presentation
Claimant QRG (PDF)
Approver QRG (PDF)

## Sheet2 (hidden)
Not started
In progress
Complete